## Detail Schedules
UAD-UiTM Schedule of Joint Thesis Supervision
Batch four (March 27nd - June 19th,2021)
NO | DATE | HOURS | ACTIVITIES | PIC | REMARKS
1 | 15 & 16-March-2021 | 8:00-12:00 | Online Proposal /Title Defence with UAD team | Head of Department | All students should have submitted 3 copies of thesis proposal 4 days prior to the proposal exam
2 | 2021-03-25 | 9:00-12:00 | Online Proposal /Title Defence with UiTM | Dr.Badli and team | Zoom meeting will be provided by UiTM
3 | 2021-03-26 | 8:00-16:00 | Revising the proposal | Each Student | Submit to the Department
4 | 2021-03-27 | 8:00-14:00 | Supervising chapter I | Students and supervisors | Letter of Appointment Send to UiTM
5 | 01 to 10-April-2021 | 8:00-14:00 | Supervising chapter II | Students and supervisors | on-line website
6 | 12 to 17-April-2021 | 8:00-14:00 | Supervising chapter III | Students and supervisors | on-line website
7 | 19 to 24-April-2021 | 8:00-14:00 | Supervising chapter IV | Students and supervisors | on-line website
8 | 26 to 30-April-2021 | 8:00-14:00 | Sipervising chapter IV | Students and supervisors | on-line website
9 | 03 to 08-May-2021 | 8:00-14:00 | supervising chapter V | Students and supervisors | on-line website
10 | 10 to 11-May-2021 | 8:00-12:00 | Pre-viva(Preliminary Defence) | UAD and UiTM team | Zoom meeting will be provided by UAD
| 13-14-May-2021 | Id Fitri | Id Mubarak | id Mubarak | Moslem Holiday
11 | 17 to 22-May-2021 | 8:00-16:00 | Thesis revision | Each Student | Consults the supervsior
12 | 25 & 26-May-2021 | 8:00-13:00 | Final Thesis Defence | USANT and UAD | Letter of Examiners send UiTM
13 | 2021-05-31 | 8:00-14:00 | Final Thesis Defence | UiTM and UAD | Letter of examiners send USANT
14 | 01 to 19-June-2021 | 8:00-16:00 | Final Thesis Revision | Each student | All signatures should have been collected
15 | 21 to 25-June-2021 | 08:00-14:00 | Graduation Registration | Each Student | Rector's office
16 | 2021-06-26 | 13:00-15:00 | Yudisium | Head of Department | Rector's office
17 | 28-June to 10-July-2021 | 08:00-14:00 | Certificate of Completion | Dr.Badli | UiTM
18 | 2021-07-31 | 08:00-14:00 | Convocation function/ceremony | Rector's office | Campus 4,level 9
Note:Those students supervised by UiTM supervisors will be examined by USANT panel members and vice versa.
Yogyakarta, March 15th, 2021
Head of Department
Akmal,M.Hum.,M.Sc.,Ph.D
NIY:60171044